LNTB

Leading Next-Gen Tomato Business

Project Charter, Business Case and Feasibility Study

ធម្មនុញ្ញគម្រោង ករណីអាជីវកម្ម និងការសិក្សាលទ្ធភាព

PLC & SDLC Documentation Pack

| Document ID | LNTB-PLC-001 | Version | 1.0 |
| --- | --- | --- | --- |
| Status | Baseline for implementation | Date | 2026-07-11 |
| Owner | Project Manager / Project Sponsor | Reviewer | Technical Lead / QA Lead |
| Approver | Project Sponsor / Academic Supervisor | Classification | Project Internal |

Document purpose — This controlled document defines the approved baseline for the LNTB pilot. Changes are managed through the Change Register and must preserve traceability to requirements, design, tests and acceptance evidence.

# Document Control

| Version | Date | Author/Owner | Change Summary | Status |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-07-11 | LNTB Project Team | Initial controlled draft | Draft |
| 1.0 | 2026-07-11 | LNTB Project Team | PLC/SDLC baseline for implementation | Baseline |

## Approvals

| Role | Name | Decision | Date | Signature / Evidence |
| --- | --- | --- | --- | --- |
| Project Sponsor / Supervisor | TBD | Pending | TBD | Meeting minutes or signed copy |
| Project Manager | TBD | Pending | TBD | Change/approval record |
| Technical Lead | TBD | Pending | TBD | Architecture review record |
| QA Lead | TBD | Pending | TBD | Quality gate record |

# 1. Executive Summary

LNTB will develop and pilot a Khmer-first smart tomato farming system for Cambodian net houses. ESP32 sensor and camera nodes, a Laravel backend and a Flutter Android application will automate safe irrigation, measure actual water and electricity usage, detect tomato ripeness and maintain a digital farm logbook. The pilot is intended to improve decision quality, reduce avoidable resource use and demonstrate a practical, maintainable architecture.

Critical baseline correction — Actual m³ and kWh cannot be measured from pump runtime alone. The pilot baseline adds a calibrated water-flow meter and electrical-energy meter. Runtime-based estimates may be retained only as a clearly labelled fallback.

# 2. Problem Statement and Opportunity

| Observed Problem | Operational Effect | Project Response |
| --- | --- | --- |
| Irrigation relies on visual judgement and manual timing | Over/under watering, labour, variable growth | Soil-moisture sensing, configurable thresholds and safe automatic control |
| Harvest readiness is checked manually across many fruits | Inconsistent picking, labour and avoidable spoilage | Camera capture, backend AI classification and confidence-aware farmer review |
| Water and electricity consumption are not recorded accurately | Unknown cost per day/season and weak profitability decisions | Metered event usage, daily rollups and configurable tariffs |
| Records are paper-based or absent | Poor comparison and traceability | Khmer digital logbook with offline cache and date filters |

# 3. SMART Objectives and Success Measures

| Objective | Target / Measure | Evidence |
| --- | --- | --- |
| Deliver an integrated pilot | Sensor node, camera, backend and Android app operate end-to-end by final demonstration | Release manifest and demonstration checklist |
| Safe irrigation | Automatic and manual irrigation never exceed configured maximum runtime; local fail-safe works offline | Safety test evidence and event logs |
| Measured resource usage | Water and electricity meters calibrated to within ±5% under pilot conditions | Calibration records and comparison tests |
| Timely data | 95% of online sensor readings visible in the app within 5 seconds | Telemetry latency report |
| Reliable field operation | System buffers at least 24 hours of readings and synchronizes without duplicates | Offline/restore test report |
| Usable Khmer experience | At least 80% of pilot users complete core tasks without assistance after training | Usability/UAT results |
| AI decision support | Validation target ≥85% macro F1 on a held-out, representative dataset; confidence and image shown | Model card and validation report |
| Benefits evidence | Measure baseline vs pilot water, energy, labour and loss indicators; no unsupported savings claim | Benefits register and closure report |

# 4. Scope

| In Scope | Out of Scope for MVP |
| --- | --- |
| One pilot net house; multi-farm-capable data model | Commercial-scale rollout or formal 24/7 SLA |
| ESP32 sensors, ESP32-CAM, pump/fan/servo control and safety enclosure | Autonomous agricultural decisions beyond approved thresholds |
| Laravel API, MySQL, Reverb, queues, scheduler, notifications and private image storage | iOS release and public app-store commercialization |
| Flutter Android application in Khmer; offline last-known state | Full farm ERP, inventory, payroll or marketplace |
| Backend-side ripeness inference and farmer verification | 100% fruit coverage or guaranteed 100% classification accuracy |
| Pilot training, field calibration, UAT, handover and closure | Permanent hardware maintenance after agreed support period |

# 5. Options Analysis

| Option | Benefits | Constraints | Decision |
| --- | --- | --- | --- |
| A. Manual process only | Lowest initial cost | No automation, measurements or learning; does not meet objectives | Reject |
| B. Sensors + local display | Works without cloud | Weak remote access, history, notifications and centralized tuning | Reject as complete solution |
| C. Integrated IoT + Laravel + Flutter + backend AI | Remote control, traceable history, configurable logic, maintainable modules | Requires networking, security and operations discipline | Selected |
| D. Fully on-device AI | Lower image transfer and cloud compute | ESP32-CAM compute/memory limits and harder model lifecycle | Defer; evaluate later |

# 6. Feasibility Assessment

| Dimension | Assessment | Conditions / Mitigation |
| --- | --- | --- |
| Technical | Feasible for pilot | Use modular design, backend inference, calibrated sensors, local safety fallback and staged integration. |
| Operational | Feasible with training | Khmer-first UI, icons, simple workflows, manual override and clear offline/stale indicators. |
| Economic | Feasible as prototype; revised BOM required | Original $103.50 excludes accurate flow/energy measurement and contingency. Budget is re-baselined after quotations. |
| Schedule | Feasible with scope control | Prioritize vertical slice, use simulated devices early and gate AI quality separately. |
| Legal / ethical | Manageable | Obtain permission for farm images/data; minimize personal data; document retention and access. |
| Environmental / safety | Manageable with controls | Waterproof enclosure, electrical isolation, rated relay, safe pump runtime, manual cutoff and field inspection. |

# 7. Initial Budget Baseline

| Cost Group | Original / Baseline | Planning Adjustment | Control |
| --- | --- | --- | --- |
| Original listed hardware and prototype services | $103.50 | Retained as source estimate | Validate vendor prices and quantities |
| Water-flow meter | Not included | $8–$20 planning allowance | Select food/irrigation-compatible calibrated device |
| Electrical-energy meter | Not included | $12–$30 planning allowance | Use isolated, appropriately rated meter/module |
| Power protection, enclosure and connectors | Partially included | $15–$30 contingency | Electrical and moisture safety first |
| Project contingency | Not included | 10–15% after quotations | Sponsor approval required for use |

Budget status — The approved cost baseline is established only after procurement quotations, safety review and sponsor approval. The original $103.50 remains a historical estimate, not a guaranteed final cost.

# 8. Milestones and Stage Gates

| Gate | Exit Evidence | Decision Authority |
| --- | --- | --- |
| G0 — Initiation | Approved charter, stakeholder map and initial risk register | Sponsor |
| G1 — Requirements | Approved SRS, acceptance criteria and traceability baseline | Product Owner / Sponsor |
| G2 — Design | Architecture, hardware safety, data, API, UX and security reviews complete | Technical Lead |
| G3 — Build Complete | Integrated release candidate, code review and unit/component tests pass | Technical Lead / QA |
| G4 — Pilot Ready | Calibration, security, backup, deployment and field safety checks pass | Sponsor / QA |
| G5 — Acceptance | UAT, benefits results, known-issue acceptance and handover complete | Product Owner / Sponsor |
| G6 — Closure | Closure report, lessons, archive and post-pilot ownership agreed | Sponsor |

# 9. Constraints, Assumptions and Dependencies

Intermittent rural connectivity is expected; core irrigation safety must not depend on cloud availability.

One camera provides representative sampling, not comprehensive inspection of every tomato.

Farm representatives are available for thresholds, data collection, usability testing and UAT.

Android device, Wi-Fi coverage, safe electrical supply and a suitable net-house installation point are available.

Laravel, Flutter and ESP32 dependencies are pinned and supported for the pilot release.

# 10. Stop / Re-plan Conditions

Pump, relay, wiring or enclosure cannot meet safety requirements.

Measurement accuracy cannot be calibrated within agreed tolerance.

AI dataset is too small or biased to support responsible validation.

No field partner or consent is available for pilot data and images.

Critical schedule or budget variance exceeds approved tolerance without a viable recovery plan.

# Authoritative References

| ID | Source | Use |
| --- | --- | --- |
| SRC-01 | LNTB Khmer proposal | Goals, scope, BOM and timeline |
| SRC-02 | LNTB requirements | Functional/non-functional baseline |
| SRC-03 | LNTB project structure | Initial architecture, data and APIs |
| SRC-04 | Official Laravel docs | Backend implementation baseline |
| SRC-05 | Official Flutter docs | Mobile architecture/quality baseline |
| SRC-06 | Official Espressif docs | ESP32 hardware/network constraints |