LNTB

Leading Next-Gen Tomato Business

Project Management Plan

ផែនការគ្រប់គ្រងគម្រោង

PLC & SDLC Documentation Pack

| Document ID | LNTB-PMP-001 | Version | 1.0 |
| --- | --- | --- | --- |
| Status | Baseline for implementation | Date | 2026-07-11 |
| Owner | Project Manager | Reviewer | Technical Lead / QA Lead |
| Approver | Project Sponsor / Academic Supervisor | Classification | Project Internal |

Document purpose — This controlled document defines the approved baseline for the LNTB pilot. Changes are managed through the Change Register and must preserve traceability to requirements, design, tests and acceptance evidence.

# Document Control

| Version | Date | Author/Owner | Change Summary | Status |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-07-11 | LNTB Project Team | Initial controlled draft | Draft |
| 1.0 | 2026-07-11 | LNTB Project Team | PLC/SDLC baseline for implementation | Baseline |

## Approvals

| Role | Name | Decision | Date | Signature / Evidence |
| --- | --- | --- | --- | --- |
| Project Sponsor / Supervisor | TBD | Pending | TBD | Meeting minutes or signed copy |
| Project Manager | TBD | Pending | TBD | Change/approval record |
| Technical Lead | TBD | Pending | TBD | Architecture review record |
| QA Lead | TBD | Pending | TBD | Quality gate record |

# 1. Delivery Approach

LNTB uses a hybrid approach: stage gates control approval and risk, while two-week engineering iterations produce demonstrable increments. Each iteration includes planning, design refinement, implementation, review, testing and a working demonstration. Hardware and AI work use experiment records because calibration and model quality require empirical evidence.

# 2. Life-Cycle Tailoring

| PLC Stage | SDLC Activities | Primary Outputs | Exit Gate |
| --- | --- | --- | --- |
| Initiation | Discovery and feasibility | Charter, business case, stakeholder map, initial RAID | G0 |
| Planning | Requirements and acceptance planning | PMP, SRS, estimates, schedule, RACI, RTM | G1 |
| Design | Architecture, data, API, hardware, UX, security | Approved design baselines and ADRs | G2 |
| Execution | Iterative firmware/backend/mobile/AI build | Reviewed code, prototypes, unit/component tests | G3 |
| Monitoring & Control | RAID, metrics, change, quality, budget and schedule control | Status reports, registers, corrective actions | Continuous |
| Validation & Pilot | Integration, calibration, system test, UAT and field pilot | Test reports, pilot evidence, acceptance decision | G4/G5 |
| Closure | Handover, lessons, archive and benefits review | Closure report, operations ownership, backlog | G6 |

# 3. Work Breakdown Structure

| WBS | Work Package | Deliverables | Owner |
| --- | --- | --- | --- |
| 1.0 | Project governance | Charter, plans, registers, stage gates | Project Manager |
| 2.0 | Requirements and UX | SRS, use cases, wireframes, localization catalogue | BA / UX Lead |
| 3.0 | Architecture and security | Architecture, API/data design, threat model, ADRs | Technical Lead |
| 4.0 | Hardware and firmware | Wiring, enclosure, firmware, calibration, device provisioning | IoT Lead |
| 5.0 | Backend | Laravel API, auth, ingestion, commands, Reverb, FCM, jobs, storage | Backend Lead |
| 6.0 | Mobile | Flutter app, Riverpod, GoRouter, cache, localization, notifications | Mobile Lead |
| 7.0 | AI | Dataset, annotation, training, validation, inference service, model card | AI Lead |
| 8.0 | Quality and integration | Test automation, system tests, performance, security, defect control | QA Lead |
| 9.0 | Deployment and pilot | Environments, release, field installation, monitoring, UAT | Ops / PM |
| 10.0 | Training and closure | Training, handover, benefits evaluation, closure archive | PM / Trainer |

# 4. Baseline Schedule

| Period | Primary Focus | Milestone / Dependency |
| --- | --- | --- |
| May 2026 | Discovery, farmer problem validation, initial data collection | G0 charter approval |
| June 2026 | Requirements, architecture, UX, BOM, procurement and simulated API | G1/G2 approval; hardware ordered |
| July 2026 — Weeks 1–2 | Backend foundation, device simulator, firmware sensor readout, Flutter skeleton | Vertical slice: reading → dashboard |
| July 2026 — Weeks 3–4 | Commands, meters, offline buffer, ripeness upload/inference, notifications | Integrated release candidate |
| August 2026 — Weeks 1–2 | Calibration, system/security/performance tests, pilot installation | G4 pilot-ready decision |
| August 2026 — Weeks 3–4 | Pilot, UAT, benefits review, final presentation and handover | G5/G6 acceptance and closure |

# 5. Iteration Management

| Event | Purpose | Participants | Evidence |
| --- | --- | --- | --- |
| Iteration planning | Select work linked to approved requirements; confirm acceptance and capacity | Delivery team + Product Owner | Iteration backlog |
| Daily coordination | Surface blockers and safety/quality concerns | Delivery team | Issue updates |
| Design / code review | Validate maintainability, security, tests and compatibility | Peer + Technical Lead | Pull request / review record |
| Demonstration | Show working increment using realistic data | Team + Product Owner | Demo notes and decisions |
| Retrospective | Improve process and controls | Delivery team | Actions with owner/date |

# 6. Scope, Schedule and Cost Control

| Control Area | Baseline | Tolerance | Action on Variance |
| --- | --- | --- | --- |
| Scope | Approved SRS and out-of-scope list | No unapproved requirement | Raise change request and update RTM |
| Schedule | WBS milestones and gate dates | ≤5 working days at work-package level | Recovery plan; escalate if critical path affected |
| Cost | Approved BOM/procurement baseline | ≤10% total forecast variance | Requote, descale or sponsor-approved change |
| Quality | Exit criteria and critical defect threshold | Zero open critical safety/security defects | Stop release; corrective action and re-test |

# 7. Resource and Procurement Plan

Assign named owners for project management, backend, mobile, IoT, AI, QA, operations and farmer validation; one person may hold multiple roles but incompatible approvals should be separated where practical.

Procurement uses an approved BOM, at least one technical review, compatibility and safety criteria, quotations and receipt inspection.

Critical spares: one ESP32, one soil sensor, relay, connectors, fuse and protected power supply.

Licenses and cloud services must have an owner, free-tier/expiry check, renewal decision and data-export path.

# 8. Monitoring and Reporting

| Metric | Target / Trigger | Source | Owner |
| --- | --- | --- | --- |
| Requirements implemented and verified | Trend by module; no orphan requirement at acceptance | RTM | BA / QA |
| Milestone variance | Escalate >5 working days | WBS schedule | PM |
| Budget forecast variance | Escalate >10% | Budget register | PM |
| Critical/high defects | 0 critical; high defects require accepted plan | Defect register | QA |
| Telemetry delivery latency | 95% ≤5 seconds while online | Observability report | Backend/Ops |
| Device sync completeness | ≥99% records reconciled after reconnect | Integration report | IoT/Backend |
| Test pass rate | ≥95% overall and 100% safety/security release tests | Test report | QA |

# 9. Gate Readiness Checklist

| Question | Required Answer |
| --- | --- |
| Are deliverables identified, versioned, reviewed and approved? | Yes |
| Are open risks/issues within approved tolerance? | Yes, or explicitly accepted by authority |
| Is traceability complete for the gate scope? | Yes |
| Are safety, security, privacy and data-retention impacts assessed? | Yes |
| Are test and acceptance results reproducible? | Yes |
| Is rollback/recovery possible for the next stage? | Yes |
| Are owners, budget and next-stage resources confirmed? | Yes |

# Authoritative References

| ID | Source | Use |
| --- | --- | --- |
| SRC-01 | LNTB Khmer proposal | Goals, scope, BOM and timeline |
| SRC-02 | LNTB requirements | Functional/non-functional baseline |
| SRC-03 | LNTB project structure | Initial architecture, data and APIs |
| SRC-04 | Official Laravel docs | Backend implementation baseline |
| SRC-05 | Official Flutter docs | Mobile architecture/quality baseline |
| SRC-06 | Official Espressif docs | ESP32 hardware/network constraints |