LNTB

Leading Next-Gen Tomato Business

Stakeholder, Communication, RACI and Change Control Plan

ផែនការភាគីពាក់ព័ន្ធ ទំនាក់ទំនង RACI និងការគ្រប់គ្រងការផ្លាស់ប្តូរ

PLC & SDLC Documentation Pack

| Document ID | LNTB-STA-001 | Version | 1.0 |
| --- | --- | --- | --- |
| Status | Baseline for implementation | Date | 2026-07-11 |
| Owner | Project Manager / Business Analyst | Reviewer | Technical Lead / QA Lead |
| Approver | Project Sponsor / Academic Supervisor | Classification | Project Internal |

Document purpose — This controlled document defines the approved baseline for the LNTB pilot. Changes are managed through the Change Register and must preserve traceability to requirements, design, tests and acceptance evidence.

# Document Control

| Version | Date | Author/Owner | Change Summary | Status |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-07-11 | LNTB Project Team | Initial controlled draft | Draft |
| 1.0 | 2026-07-11 | LNTB Project Team | PLC/SDLC baseline for implementation | Baseline |

## Approvals

| Role | Name | Decision | Date | Signature / Evidence |
| --- | --- | --- | --- | --- |
| Project Sponsor / Supervisor | TBD | Pending | TBD | Meeting minutes or signed copy |
| Project Manager | TBD | Pending | TBD | Change/approval record |
| Technical Lead | TBD | Pending | TBD | Architecture review record |
| QA Lead | TBD | Pending | TBD | Quality gate record |

# 1. Stakeholder Register

| Stakeholder | Interest / Need | Influence | Engagement Strategy | Owner |
| --- | --- | --- | --- | --- |
| Project Sponsor / Academic Supervisor | Outcomes, feasibility, evidence, budget and final presentation | High | Gate approvals, concise weekly status and escalation | PM |
| Farmer / Net-house Operator | Safe, simple Khmer workflows, dependable irrigation and useful cost data | High | Co-design, field observation, demonstrations, UAT and training | Product Owner |
| Project Team | Clear scope, interfaces, priorities and decisions | High | Daily coordination, shared registers and iteration reviews | PM |
| Technical / Architecture Lead | Maintainable, secure and testable design | High | Design reviews, ADRs, pull-request approval | Technical Lead |
| Hardware Suppliers / Cloud Providers | Clear specifications, orders and service constraints | Medium | Procurement records, compatibility checks and expiry monitoring | PM / Ops |
| Institution / Program Partners | Compliance, learning, visibility and reporting | Medium | Milestone summaries and final evidence package | Sponsor |
| Future Support Owner | Operability, documentation, backups and known issues | Medium | Early operations review, handover and support runbook | Operations Lead |

# 2. Communication Matrix

| Communication | Audience | Cadence | Channel / Format | Owner | Record |
| --- | --- | --- | --- | --- | --- |
| Delivery status | Sponsor, leads, Product Owner | Weekly | One-page status: RAG, progress, forecast, RAID, decisions | PM | Status archive |
| Iteration planning/review | Delivery team, Product Owner | Every 2 weeks | Meeting + working demo | PM | Backlog/demo notes |
| Architecture review | Technical, security, QA leads | At design changes | Review meeting + ADR | Technical Lead | Approved ADR |
| Field/pilot coordination | Farmer, IoT, QA, PM | Before and during pilot | Khmer briefing + checklist | PM | Site/pilot log |
| Incident escalation | Sponsor, technical, operations, affected users | As required | Phone/chat + incident record | Incident Lead | Incident report |
| Gate review | Approvers and owners | At each gate | Evidence pack + decision meeting | PM | Gate decision |

# 3. RACI Matrix

| Activity | Sponsor | PM | PO/Farmer | Tech | IoT | Backend | Mobile | AI | QA | Ops |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approve charter/scope | A | R | C | C | I | I | I | I | C | I |
| Elicit/approve requirements | I | A | R | C | C | C | C | C | C | I |
| Approve architecture/security | I | C | C | A/R | C | R | R | R | C | C |
| Hardware safety/calibration | I | C | C | A | R | C | I | I | R | C |
| Backend implementation | I | I | C | A | C | R | C | C | C | C |
| Mobile implementation/UX | I | I | C | A | I | C | R | I | C | I |
| AI dataset/model validation | I | C | C | A | C | C | I | R | R | I |
| System test/release recommendation | I | C | C | C | C | C | C | C | A/R | C |
| Pilot acceptance | A | R | R | C | C | C | C | C | C | C |
| Deployment/operations handover | I | C | C | A | C | C | C | C | C | R |
| Change approval — major | A | R | C | C | I | I | I | I | C | I |

R = Responsible, A = Accountable, C = Consulted, I = Informed. Each activity must have exactly one accountable role.

# 4. Change-Control Procedure

Submit a change request with problem/opportunity, proposed outcome, urgency and affected baseline items.

Log and classify the request: corrective, preventive, scope, design, safety, security, regulatory, budget or schedule.

Assess impacts on requirements, architecture, hardware, data, security, UX, tests, budget, schedule, operations and training.

Obtain decision from the applicable authority; no implementation before approval except emergency safety action.

Plan and implement on a controlled branch/work item; update documents and traceability.

Verify through review and regression testing; obtain acceptance and update release notes.

Close the change with evidence, effective version and stakeholder communication.

# 5. Change Authority

| Change Class | Examples | Authority | Required Evidence |
| --- | --- | --- | --- |
| Minor | Clarification with no scope, safety, interface, budget or acceptance impact | Document owner + reviewer | Impact statement and version update |
| Standard technical | Backward-compatible implementation/design refinement within baseline | Technical Lead + QA | ADR or review record; regression tests |
| Major | New/removed requirement, milestone/budget change, interface break, acceptance change | Sponsor / Change Control Board | Full impact assessment and updated baselines |
| Safety / Security Emergency | Pump hazard, exposed credential, active data compromise | Incident Lead may authorize immediate containment; sponsor ratifies | Incident timeline, containment, root cause, tests and retrospective approval |

# 6. Issue Escalation

| Severity | Definition | Response / Escalation |
| --- | --- | --- |
| Critical | Immediate safety risk, uncontrolled pump, credential compromise, data loss or pilot blocked | Stop affected operation; notify PM/Tech/Sponsor immediately; incident record within 1 hour |
| High | Major function unavailable or release criterion failed with no practical workaround | Owner within 4 hours; corrective plan within one working day |
| Medium | Degraded function with workaround; limited scope/schedule impact | Plan in current/next iteration |
| Low | Cosmetic, documentation or improvement request | Backlog prioritization |

# 7. Initial Architecture Decisions

| ADR | Decision | Rationale / Consequence |
| --- | --- | --- |
| ADR-001 | Backend-side AI inference for MVP | Simplifies model lifecycle and avoids ESP32-CAM compute limits; requires private image upload/storage. |
| ADR-002 | Laravel owns configurable thresholds; firmware stores safe fallback | Central tuning while preserving offline safety. |
| ADR-003 | Single-farm MVP UX; multi-farm-capable schema | Reduces UI complexity without costly redesign later. |
| ADR-004 | Add calibrated flow and energy meters | Supports actual m³/kWh claims; revises BOM. |
| ADR-005 | Store-and-forward with idempotency keys | Prevents data loss and duplicate readings after network recovery. |
| ADR-006 | Khmer ARB localization; no hardcoded user strings | Supports consistent translation and testing. |
| ADR-007 | Private media storage with retention policy | Reduces image exposure and supports controlled AI evidence. |

# 8. Meeting and Decision Rules

Agendas identify the decision required, owner and evidence before the meeting.

Minutes record decisions, assumptions, actions, owner, due date and any dissent or conditions.

Unresolved decisions receive an ID and due date; verbal decisions that alter a baseline are not effective until recorded.

Farmer-facing materials and field instructions are provided in Khmer or explained in Khmer.

# Authoritative References

| ID | Source | Use |
| --- | --- | --- |
| SRC-01 | LNTB Khmer proposal | Goals, scope, BOM and timeline |
| SRC-02 | LNTB requirements | Functional/non-functional baseline |
| SRC-03 | LNTB project structure | Initial architecture, data and APIs |
| SRC-04 | Official Laravel docs | Backend implementation baseline |
| SRC-05 | Official Flutter docs | Mobile architecture/quality baseline |
| SRC-06 | Official Espressif docs | ESP32 hardware/network constraints |