LNTB

Leading Next-Gen Tomato Business

Training, Pilot Evaluation and Project Closure Plan

ផែនការបណ្តុះបណ្តាល វាយតម្លៃសាកល្បង និងបិទគម្រោង

PLC & SDLC Documentation Pack

| Document ID | LNTB-CLS-001 | Version | 1.0 |
| --- | --- | --- | --- |
| Status | Baseline for implementation | Date | 2026-07-11 |
| Owner | Project Manager / Product Owner | Reviewer | Technical Lead / QA Lead |
| Approver | Project Sponsor / Academic Supervisor | Classification | Project Internal |

Document purpose — This controlled document defines the approved baseline for the LNTB pilot. Changes are managed through the Change Register and must preserve traceability to requirements, design, tests and acceptance evidence.

# Document Control

| Version | Date | Author/Owner | Change Summary | Status |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-07-11 | LNTB Project Team | Initial controlled draft | Draft |
| 1.0 | 2026-07-11 | LNTB Project Team | PLC/SDLC baseline for implementation | Baseline |

## Approvals

| Role | Name | Decision | Date | Signature / Evidence |
| --- | --- | --- | --- | --- |
| Project Sponsor / Supervisor | TBD | Pending | TBD | Meeting minutes or signed copy |
| Project Manager | TBD | Pending | TBD | Change/approval record |
| Technical Lead | TBD | Pending | TBD | Architecture review record |
| QA Lead | TBD | Pending | TBD | Quality gate record |

# 1. Training Objectives and Audiences

| Audience | Required Competence | Method / Material | Verification |
| --- | --- | --- | --- |
| Farmer operator | Interpret live/stale status, use safe irrigation, review ripeness/cost, respond to alerts and use manual fallback | Khmer demonstration, pictorial quick guide, supervised practice | Scenario checklist completed without unsafe action |
| Farm manager / Product Owner | Configure approved thresholds/tariffs, review logs and accept outcomes | Workshop and controlled settings exercise | Configuration/UAT scenarios pass |
| Technician / IoT support | Safe shutdown, inspection, provisioning, calibration and firmware recovery | Technical runbook + bench practice | Observed practical assessment |
| Backend/mobile/AI team | Deploy, monitor, restore, troubleshoot and release compatible components | Runbooks, architecture and release rehearsal | Deployment/restore exercise passes |
| Project sponsor / reviewers | Understand objectives, evidence, limitations, benefits and residual risks | Decision brief and final demonstration | Gate/acceptance decision recorded |

# 2. Farmer Training Curriculum

| Module | Content | Duration / Evidence |
| --- | --- | --- |
| T1 — System and safety | What the system does/does not do; physical cutoff; never service energized wiring; manual fallback | 20 min + questions |
| T2 — Dashboard | Status labels/icons, values/units, last updated, stale/offline and sensor quality | 20 min + identification exercise |
| T3 — Irrigation | Automatic/manual mode, confirmation, queued/running/completed/failed, stop and max runtime | 30 min + supervised start/stop |
| T4 — Ripeness | Image, class, confidence, limitations and manual verification | 15 min + example review |
| T5 — Usage/logbook | Measured vs estimated, day/month/season view and filters | 20 min + locate a record |
| T6 — Alerts/support | Notification severity, safe response, support information and incident reporting | 15 min + alert scenario |
| T7 — Account/privacy | Sign in/out, phone loss, image/data use and permissions | 10 min + sign-out demonstration |

# 3. Pilot Design

| Element | Baseline |
| --- | --- |
| Site / participants | One approved tomato net house and named farmer/operator; record relevant cultivation context. |
| Duration | Minimum two representative weeks after calibration, or longer if needed to observe irrigation/ripeness conditions. |
| Comparison | Record pre-pilot baseline and pilot-period water, energy, labour/inspection, irrigation incidents and harvest-quality indicators. |
| Scope | Sensor/meter telemetry, automatic/manual irrigation, offline recovery, dashboard, ripeness support, usage/cost, logbook and alerts. |
| Instrumentation | Calibrated flow/energy reference; device/service logs; user task sheets; issue/incident register. |
| Support | Named daily contact, safe shutdown procedure, spares and escalation path. |
| Ethics/privacy | Farmer permission, purpose explanation, private image handling and approved presentation use. |

# 4. Pilot Activities

Confirm site safety, power, Wi-Fi, physical cutoff, enclosure, calibration and participant permission.

Capture baseline process and resource measurements before automation where feasible.

Train users and complete supervised competency checklist.

Run controlled commissioning scenarios: telemetry, manual start/stop, max runtime, offline mode, replay, alerts and restore contact.

Operate pilot, review health daily and record interventions, defects, incidents and user feedback.

Collect ripeness samples/manual labels under representative conditions and review model disagreements.

Reconcile data completeness, measured usage, cost calculations and benefits indicators.

Conduct UAT, known-issue review, acceptance decision, handover and closure/next-phase recommendation.

# 5. Benefits and KPI Evaluation

| KPI | Definition / Calculation | Evidence / Interpretation |
| --- | --- | --- |
| Water use per day/event | Calibrated m³ from flow meter; compare normalized baseline where possible | Report observed value and context; do not assume 20–30% saving |
| Energy use per event/day | Calibrated kWh from meter | Compare pump operation and tariff-derived cost |
| Avoided manual checks | Baseline vs pilot time/frequency for irrigation and ripeness inspection | Self-report + observation; note changed workload |
| Irrigation safety/reliability | Unsafe events, max-runtime activations, failed/ambiguous commands and recovery | Target zero unsafe uncontrolled event |
| Data completeness | Expected vs stored sequences/events and post-reconnect reconciliation | Target ≥99% logical records for pilot |
| Telemetry timeliness | Backend-to-dashboard latency for online samples | Target 95% ≤5 seconds |
| Usability success | Representative users completing core tasks after training | Target ≥80% without assistance |
| AI quality | Held-out macro F1 plus field-reviewed disagreements | Target ≥85% macro F1; limitations documented |
| System availability | Monitored service/device uptime and incident duration | Pilot observation; no commercial SLA claim |

# 6. Pilot Stop and Safety Criteria

Any uncontrolled pump operation, exposed unsafe wiring, water ingress or inability to isolate power.

Repeated measurement fault that makes actual usage claims unreliable.

Credential compromise, unauthorized farm access or privacy breach.

Data loss/recovery failure outside accepted continuity tolerance.

Farmer withdraws permission or field conditions make operation unsafe.

Critical defect with no immediate containment. The Project Manager/Incident Lead may suspend pilot pending review.

# 7. UAT Scenarios

| UAT ID | Scenario | Acceptance |
| --- | --- | --- |
| UAT-01 | Sign in and identify current farm status | Farmer correctly interprets live/stale status and key values |
| UAT-02 | Start and stop manual irrigation | Confirmation understood; progression/outcome visible; no duplicate/unsafe actuation |
| UAT-03 | Observe automatic irrigation/offline fallback | Event follows approved threshold and safety limits; logs reconcile |
| UAT-04 | Review ripe tomato result | Image, class/confidence and manual verification guidance understood |
| UAT-05 | Review water/energy/cost and logbook | User finds requested period and distinguishes measured/estimated |
| UAT-06 | Respond to offline/device/threshold alert | User takes documented safe action and can contact support |
| UAT-07 | Update authorized setting | Validated value/effective version saved and audit visible |
| UAT-08 | Sign out / lost phone process | Token revoked and account recovery/support path understood |

# 8. Handover Package

| Recipient | Handover Contents |
| --- | --- |
| Farmer / Product Owner | Khmer quick guide, safe-use checklist, credentials/account process, support contacts, known limitations and accepted configuration |
| Operations / Support | Architecture, inventories, deployment/runbooks, monitoring, backup/restore, incident and maintenance procedures |
| Engineering Team | Tagged source, dependency lockfiles, environments/config schema, ADRs, test evidence, backlog and known technical debt |
| Sponsor / Institution | Accepted scope, release manifest, benefits/pilot report, costs, risks, lessons and roadmap recommendation |
| Configuration Manager | Final controlled documents, registers, approvals, release/model/calibration artifacts and archive index |

# 9. Closure Checklist

| Closure Item | Completion Evidence |
| --- | --- |
| Deliverables accepted or conditionally accepted | Signed acceptance and exception/action list |
| Scope/schedule/cost reconciled | Final baseline vs actual summary with explanations |
| Risks/issues/changes/defects dispositioned | Closed, transferred or accepted with named owner/due date |
| Operations ownership transferred | Runbook walkthrough and access/inventory confirmation |
| Data/privacy actions completed | Retention/export/deletion decision and permission record |
| Procurement/assets closed | Hardware inventory, ownership and service/subscription decision |
| Lessons and benefits recorded | Retrospective and KPI/pilot report |
| Repository/archive completed | Final register, read-only baseline and recoverability check |
| Team/stakeholders notified | Closure communication and support/roadmap contact |

# 10. Initial Lessons-Learned Prompts

Which assumptions about Wi-Fi, sensors, farmer workflow and tomato images were wrong or incomplete?

Which safety, synchronization and operational controls prevented incidents or slowed delivery unnecessarily?

Which Khmer terms, icons or screens caused misunderstanding?

Which measurements support or contradict the expected cost/resource benefits?

What technical debt or vendor dependency must be resolved before a wider rollout?

What should be stopped, started and continued in the next phase?

# 11. Post-Pilot Roadmap Options

| Option | Prerequisites | Decision Evidence |
| --- | --- | --- |
| Stabilize single-farm pilot | Resolve defects, improve enclosure/calibration, extend soak/season data | Reliable operations and clear maintenance ownership |
| Multi-farm beta | Tenant authorization tests, farm selector UX, provisioning/support scale and capacity plan | Demand and support readiness |
| Improved AI coverage | Larger representative dataset, camera placement study and model monitoring | Validated gain vs field effort/cost |
| On-device/edge inference | Benchmark accuracy, memory, latency, energy and update lifecycle | Evidence that edge benefits outweigh complexity |
| Commercialization | Formal security/privacy/legal review, SLA, pricing, support, procurement and manufacturing plan | Approved business case and compliance |

# Authoritative References

| ID | Source | Use |
| --- | --- | --- |
| SRC-01 | LNTB Khmer proposal | Goals, scope, BOM and timeline |
| SRC-02 | LNTB requirements | Functional/non-functional baseline |
| SRC-03 | LNTB project structure | Initial architecture, data and APIs |
| SRC-04 | Official Laravel docs | Backend implementation baseline |
| SRC-05 | Official Flutter docs | Mobile architecture/quality baseline |
| SRC-06 | Official Espressif docs | ESP32 hardware/network constraints |