## Overview
LNTB — Smart Tomato Farming System
Requirements & Planning Workbook
Team | LNTB (Leading Next-Gen Tomato Business)
System | IoT + AI-enabled smart irrigation, ripeness detection, and cost tracking
Stack | Laravel (Backend) · Flutter (Mobile App) · Arduino / C++ on ESP32 (Firmware)
Primary UI language | Khmer (100%)
Total hardware budget | $103.50 per net house
Sheet Guide
• Requirements Matrix | All functional & non-functional requirements with ID, module, priority, and status.
• Hardware BOM | Bill of materials with quantities and cost, auto-summed budget.
• Software Stack | Technology choices by layer (Firmware / Backend / Mobile App).
• Database Schema | Tables and key fields for the Laravel/MySQL database.
• Project Timeline | Phase-by-phase schedule, May–August.

## Requirements Matrix
ID | Module | Category | Requirement | Priority | Status
FR-HW-01 | Firmware | Functional | Read soil moisture at configurable interval (default 60s). | Must | Not Started
FR-HW-02 | Firmware | Functional | Read temperature and humidity via DHT22. | Must | Not Started
FR-HW-03 | Firmware | Functional | Read ambient light level via LDR. | Must | Not Started
FR-HW-04 | Firmware | Functional | Send readings to Laravel API as JSON over HTTPS. | Must | Not Started
FR-HW-05 | Firmware | Functional | Poll Laravel command endpoint (default 10s) for pending commands. | Must | Not Started
FR-HW-06 | Firmware | Functional | Trigger relay (water pump) on pump_on / pump_off commands. | Must | Not Started
FR-HW-07 | Firmware | Functional | Trigger servo (net roof) on servo_open / servo_close commands. | Should | Not Started
FR-HW-08 | Firmware | Functional | Acknowledge executed commands back to backend. | Should | Not Started
FR-HW-09 | Firmware | Functional | Fall back to local safe moisture threshold if backend unreachable. | Should | Not Started
FR-HW-10 | Firmware | Functional | Capture tomato fruit image at configurable interval or on trigger. | Should | Not Started
FR-HW-11 | Firmware | Functional | Send captured image / inferred ripeness result to Laravel API. | Should | Not Started
FR-HW-12 | Firmware | Functional | Store WiFi credentials and API endpoint in separate config file. | Could | Not Started
FR-HW-13 | Firmware | Functional | Reconnect automatically after WiFi drop without manual reset. | Could | Not Started
FR-BE-01 | Backend | Functional | Expose authenticated endpoint for ESP32 to submit sensor readings. | Must | Not Started
FR-BE-02 | Backend | Functional | Expose endpoint for ESP32 to poll pending commands. | Must | Not Started
FR-BE-03 | Backend | Functional | Expose endpoint for ESP32 to acknowledge command execution. | Must | Not Started
FR-BE-04 | Backend | Functional | Expose endpoint to receive ripeness detection results/images. | Must | Not Started
FR-BE-05 | Backend | Functional | Calculate real-time water (m3) and electricity (kWh) usage per irrigation event. | Must | Not Started
FR-BE-06 | Backend | Functional | Scheduled job rolls up daily usage into usage_records with USD cost. | Must | Not Started
FR-BE-07 | Backend | Functional | Broadcast live sensor updates via WebSocket (Reverb) per farm channel. | Should | Not Started
FR-BE-08 | Backend | Functional | Send push notification (FCM) when fruit is ready-to-harvest. | Should | Not Started
FR-BE-09 | Backend | Functional | Send push notification when soil moisture crosses critical threshold. | Should | Not Started
FR-BE-10 | Backend | Functional | Provide Sanctum token-based authentication for Flutter app. | Should | Not Started
FR-BE-11 | Backend | Functional | Provide paginated, filterable logbook query endpoints. | Should | Not Started
FR-BE-12 | Backend | Functional | Allow farmer to manually trigger/stop irrigation via authenticated API. | Could | Not Started
FR-BE-13 | Backend | Functional | Record trigger source (auto vs manual) per irrigation event. | Could | Not Started
FR-BE-14 | Backend | Functional | Support configurable per-farm cost rates ($/m3, $/kWh). | Could | Not Started
FR-APP-01 | Mobile App | Functional | Display login screen; authenticate against Laravel Sanctum. | Must | Not Started
FR-APP-02 | Mobile App | Functional | Display real-time dashboard: moisture, temperature, humidity, light. | Must | Not Started
FR-APP-03 | Mobile App | Functional | Visually indicate status with color coding (green/red). | Must | Not Started
FR-APP-04 | Mobile App | Functional | Allow farmer to manually trigger or stop irrigation. | Must | Not Started
FR-APP-05 | Mobile App | Functional | Display current auto-irrigation status (on/off, last triggered). | Must | Not Started
FR-APP-06 | Mobile App | Functional | Display latest ripeness detection results with images and confidence. | Should | Not Started
FR-APP-07 | Mobile App | Functional | Display real-time and historical water/electricity cost. | Should | Not Started
FR-APP-08 | Mobile App | Functional | Provide digital logbook, filterable by month and year. | Should | Not Started
FR-APP-09 | Mobile App | Functional | Receive and display push notifications for alerts. | Should | Not Started
FR-APP-10 | Mobile App | Functional | Render UI 100% in Khmer language. | Should | Not Started
FR-APP-11 | Mobile App | Functional | Function acceptably on low-end/budget Android devices. | Could | Not Started
FR-APP-12 | Mobile App | Functional | Handle intermittent connectivity gracefully (cache + retry). | Could | Not Started
NFR-01 | Cross-cutting | Usability | Farmer can read dashboard status within 5 seconds via color/icon cues. | Must | Not Started
NFR-02 | Cross-cutting | Performance | Sensor readings appear on dashboard within 5 seconds (via WebSocket). | Must | Not Started
NFR-03 | Cross-cutting | Reliability | Basic auto-irrigation continues if backend is temporarily unreachable. | Must | Not Started
NFR-04 | Cross-cutting | Availability | Backend uptime suitable for single-farm pilot (no formal SLA at MVP). | Must | Not Started
NFR-05 | Cross-cutting | Security | All API traffic uses HTTPS; device endpoints use API keys, users use Sanctum. | Should | Not Started
NFR-06 | Cross-cutting | Scalability | Schema supports multiple farms/devices per user without redesign. | Should | Not Started
NFR-07 | Cross-cutting | Localization | All user-facing text sourced from Khmer .arb files, never hardcoded. | Should | Not Started
NFR-08 | Cross-cutting | Cost | Total hardware BOM per net house does not exceed ~$105 USD. | Should | Not Started
NFR-09 | Cross-cutting | Maintainability | Firmware, backend, and app structured into clearly separated modules. | Could | Not Started
NFR-10 | Cross-cutting | Data retention | Sensor readings/logs retrievable for at least one full growing season. | Could | Not Started

## Hardware BOM
# | Component | Purpose | Qty | Unit Cost (USD) | Line Total (USD)
1 | ESP32 Microcontroller Board | Main sensor node controller (hardware brain) | 1 | 7 | 7
2 | ESP32-CAM | AI camera module for ripeness evaluation | 1 | 12 | 12
3 | Soil Moisture Sensor | Soil moisture reading | 2 | 2 | 4
4 | DHT22 Temperature & Humidity Sensor | Temperature and air humidity reading | 1 | 4.5 | 4.5
5 | LDR Sensor & Servo Motor | Light reading + auto net-roof control | 1 | 6 | 6
6 | 2-Channel Relay + Water Pump + Fan | Irrigation / ventilation on-off control | 1 | 20 | 20
7 | Assembly Accessories (wiring, waterproof box, PCB) | Assembly & protection | 1 | 30 | 30
8 | Mobile App + Cloud Server Budget | Development & test server allowance | 1 | 20 | 20
| Total Estimated Budget |  |  |  | 103.5

## Software Stack
Layer | Item | Choice
Firmware | Language | C++ (Arduino Framework)
Firmware | Toolchain | PlatformIO (recommended) or Arduino IDE
Firmware | Key Libraries | DHT sensor library, ESP32Servo, HTTPClient, ArduinoJson, esp32-camera
Backend | Framework | Laravel (latest LTS-compatible version)
Backend | Auth | Laravel Sanctum
Backend | Realtime | Laravel Reverb
Backend | Database | MySQL
Backend | Notifications | Firebase Cloud Messaging
Backend | Scheduling | Laravel Scheduler (daily usage rollup)
Mobile App | Framework | Flutter
Mobile App | State Management | Riverpod
Mobile App | Routing | GoRouter
Mobile App | Realtime Client | laravel_echo + pusher_client
Mobile App | HTTP Client | Dio
Mobile App | Push Notifications | firebase_messaging
Mobile App | Localization | Flutter intl / .arb files (Khmer)

## Database Schema
Table | Column | Type | Notes
farms | id | bigint PK
| user_id | FK -> users | owner
| name | string
| location | string | nullable
devices | id | bigint PK
| farm_id | FK -> farms
| esp32_id | string, unique | hardware identifier
| type | enum | sensor_node, camera_node
| last_seen_at | timestamp | nullable
sensor_readings | id | bigint PK
| device_id | FK -> devices
| soil_moisture | decimal | %
| temperature | decimal | °C
| humidity | decimal | %
| light_level | decimal | lux / raw LDR
| recorded_at | timestamp | indexed with device_id
irrigation_events | id | bigint PK
| device_id | FK -> devices
| triggered_by | enum | auto, manual
| triggered_by_user_id | FK -> users | nullable, manual only
| duration_seconds | integer
| water_m3 | decimal
| power_kwh | decimal
| started_at / ended_at | timestamp | ended_at nullable
ripeness_results | id | bigint PK
| device_id | FK -> devices | camera node
| image_url | string
| confidence | decimal | AI confidence %
| status | enum | unripe, semi_ripe, ready_to_harvest
| detected_at | timestamp
usage_records | id | bigint PK
| farm_id | FK -> farms
| date | date
| water_m3 | decimal | sum for the day
| power_kwh | decimal | sum for the day
| cost_usd | decimal | calculated
pending_commands | id | bigint PK
| device_id | FK -> devices
| command | enum | pump_on, pump_off, servo_open, servo_close
| status | enum | pending, acknowledged, executed
users | id | bigint PK
| name | string
| phone_or_email | string | phone login may suit farmers better
| password | hashed

## Project Timeline
Month | Phase | Key Activities
May | Ideation | Team discussion, identify farmer problems, write initial project proposal, assign member tasks.
June | Design | Schematic circuit design, net-house prototype layout, app UI/UX design (Khmer), purchase hardware.
July | Build & Test | Assemble hardware, write firmware, train AI on ripeness images, build app, field-test in real net house.
August | Finalize | Refine system based on test results, calculate savings, prepare and deliver final presentation.